## Sample Timeline
SUDC FOUNDATION EVENT MANAGEMENT TIMELINE SAMPLE
15 WEEKS PRIOR
Host an initial planning meeting with all key stakeholders
Pre- planning meeting thoughts
Who is your target audience for the event?
What are you trying to accomplish/ Advocacy? Fundraising?
What type of event are you planning? 5k, vendor fair, bowling, gala, etc.?
Where will the event be held? What dates do they have available?
Select date and time for event
Ensure VIPs such as local congressmen or the mayor and/or speakers are available for selected date
Consult community and school calendar/religious calendars to avoid conflicts
Set budget
Refer to the budget planning template on the SUDC.org event page
Identify potential funding sources
What corporations or companies do business in your community for potential sponsorship or in-kind donations?
Who do you personally know that works for a corporation or company in your community?
How many friends, family members and community businesses or organizations will financially support the event?
Reserve the venue
Consider Parking availability/restrictions
Other events occurring near space - will they conflict?
What are the access times to space?
What is any equipment is included with room rental?
Are there security issues? Fire Marshall limitations?
What are the facility contract and/or liability insurance requirements? If the event is hosted on behalf of the SUDC Foundation, refer these documents and questions to SUDC Foundation staff
Fundraising ideas
Raffles? Silent Auction? Live Auction? Permit or license needs? If the event is hosted on behalf of the SUDC Foundation, refer these documents and questions to Assistant Executive Director.
Establish committees and chair-people
Committee examples include: Publicity, Venue Logistics, Auction solicitation, Sponsorships. Reminder to select chair-people based on their skills sets not personal relationships.
Tip* the SUDC Foundation Run for a Reason Kit is a good resource for committee tasks and responsibilities
Tip* encourage committee chair-people meet regularly with their committees throughout the planning process
Event timeline
Create your timeline and delegate responsibilities, be sure to include bi-monthly and weekly update meetings as the event draws near.
12 WEEKS PRIOR
Planning meeting with chair-people should be scheduled Monthly
Promotional/Publicity Planning
Notify SUDC Foundation staff of your plans. Staff will have a planning call with you to discuss overall management of the event and offer suggestions of services the foundation can provide for assistance.
Request to SUDC Foundation staff event updates on your child's SUDC memorial site this may include a run sign up page if applicable
Select designer/printer for T-shirts and other promotional. * SUDC Foundation logo is available upon request, designs with the SUDC Foundation logo must be approved by SUDC Foundation staff.
Determine if large-scale promotional items will need to be designed and made (i.e. large signs, posters, etc.)
Set up a communication plan and schedule, include social media posts for the duration of the next 12 twelve weeks. Refer to the SUDC Foundation Publicity Tips Tool Kit for ideas
Plan for a live web stream, schedule photographer and videographer day of the event
Send Save-the-Date cards or emails to everyone you think will participate
Volunteer Recruitment Planning
Encourage committee chairs to select volunteers to support their committee work
Consider appropriate ages, physical limitations and skill sets when assigning volunteer responsibilities
Refer to the Volunteer assignment template on the SUDC.org event planning page
10 WEEKS PRIOR
Planning meeting with chair-people should be scheduled Monthly
Secure Equipment
Secure A/V needs for event; lighting, microphone, sound system
Portable stage and podiums is applicable
Secure timing company if hosting a Run for a Reason
Data processing for credit cards: readers, computers, processors
Promotional Items
Begin designing printed pieces (i.e. invitations, tickets, flyers, programs, pamphlets, program booklets, etc.)
Publicity
Develop press release
Develop PSA Announcements
Request and receive speakers’/VIPs’ bios
Add event to local community and school calendars, discuss other local promotion opportunities
Hospitality Needs
Select & book caterer or plan food and beverage needs
Design and create/order invitations, flyers etc.
Secure entertainment/musicians
Order plants/flowers and additional décor materials
Reserve additional set-up materials
8 WEEKS PRIOR
Planning meeting with chair-people should be scheduled bi-Monthly
Promotional Items
Review printed materials and program with your designer, begin editing process
Determine if awards/trophies will be given away, order any giveaways
Order T-Shirts based on design approved by the SUDC Foundation
Venue Logistics
Determine parking: confirm attendants or local police department for assistance
Obtain directional maps for visitors to include with invitation
Arrange for transportation (buses, shuttles) if necessary from a centralized parking location
Confirm accessibility resources for handicapped including restrooms
Confirm permits, contracts and liability insurance documents have been processed
Publicity
Release press announcements to national and local print media
Continue social media posts
Hospitality Needs
Set menu with caterer – know that you can confirm the final head count approx. a week prior to the event
Send out invitations/eblasts, be sure to create a tracking system for responses
6 WEEKS PRIOR
Planning meeting with chair-people should be scheduled bi-monthly
Venue Logistics
Hold walk-through with major stakeholders/committee members to ensure all needs are met
Secure musicians/entertainers sound check
Order extra trash receptacles, recycling bins, portable restrooms if necessary
Publicity
Distribute flyers/email blasts advertising event
Hospitality Needs
Finalize transportation logistics for VIPs
Assign a personal volunteer for each VIP guest to ensure the guests needs are met
Purchase all needed decorations, other than flower arrangements if not previously ordered
4 WEEKS PRIOR
Planning meeting with chair-people should be held weekly
Volunteer Management
Confirm with committee chairs all volunteers have an assignment for each aspect of the event
Create volunteer duty form
Schedule volunteer training
Venue Logistics | Make parking and directional signs that can be created in-house
Confirm security needs and plan walk-through of site with them
Coordinate with the SUDC Foundation staff if applicable and vendors on when payment will be received (in most cases after services are rendered)
Hospitality Needs
Create welcome packets/materials for attendees
Create script for yourself or for VIPs/presenters
Create seating plans and room diagrams for assistance with set-up and day-of-event questions
2 WEEKS PRIOR
Planning meeting with chair-people should be scheduled weekly
Venue Logistics
Hold pre-event meeting with all significant stakeholders (vendors, managers of venue, key committee members and volunteers, etc.)
Do one last walk-through of venue
Confirm set-up/breakdown times and procedures with all vendors
Recheck all equipment/materials to ensure nothing is damaged, quantity is correct, etc.
Confirm data processing needs for accepting credit cards
Promotional Items
Ensure all printed materials/collateral are printed, assembled and correct from errors
Publicity
Photo/Video check list, identify key participants to capture
Make follow-up calls to media asking them to confirm attendance
Post to social media and/or email final information for participants, including directions, maps, last minute details, etc.
Hospitality Needs
Make nametags/lanyards of attendees and extra plain ones for surprise guests
Create "Event Day Survival Kit" full of needed items: pens, sharpies, tape, scissors, etc.
Ensure all appropriate contacts' info is listed where you can easily retrieve it
Create detailed hour-by-hour event agenda (event plan) for chair people/vendors and distribute to them
Follow-up with RSVP list - make personalized phone calls & emails, if necessary
Send final numbers to the caterer
Confirm participation with all VIPs/presenters. Send them updated event details, run of shows, and talking points.
24 Hours Out
Venue Logistics | Set-up registration area, if possible, so you are prepared for the next day
Decorate venue if you can
Deliver materials/equipment to venue site
Test web streaming if video planning
Test computer connections including data processing for credit cards
Be prepared to troubleshoot changes day-of
Schedule last minute A/V run-through
Promotional items | Display parking/directional signs ( if weather is in climate, reschedule this for early morning of)
Hospitality Needs
Reconfirm schedule with caterer
DAY OF EVENT
Event Chairperson Oversight
Arrive 2-3 hours early and do one last walk-through
Oversee set-up for vendors, silent auction, games, etc.
Ensure all VIP materials are correctly labeled and in place, waters in podium
Check all A.V. , technical equipment and sound set ups.
2 WEEKS POST EVENT
Event Chairperson Oversight
Send thank you letters to all donors, VIP's and supporters. Tax Receipt letters will be sent by the SUDC Foundation if your event was hosted on behalf of the foundation
Manage invoices and account payables; these may be managed through the SUDC Foundation if applicable
Hold post-event meeting with key players to evaluate event
Send SUDC Foundation staff updates for your child's memorial site and SUDC Foundation public social media sites
Update personal social media sites
Regardless if your event was hosted on behalf of the foundation please complete the post event evaluation form and send in to SUDC Foundation staff for our records
Book next year's venue, for annual event